## User Stories
EPIC | USER STORY | PRIORITY | VALUE | RISK | ESTIMATE | RELEASE | ACCEPTANCE | DEPENDENCIES | REQUESTOR | NOTES | VALUE/RISK MATRIX | PRIORITY(INT) | VALUE(INT) | RISK(INT) | PRIORITY(INV) | VALUE(INV) | RISK(INV) | THEME(Sp) | FEATURE(Sp) | RELEASE(S) | ROW(S)
Unregistered User | As an unregistered user, I want to be able to visit the web application, so that I can explore the functionalities. | 1 High | 1 High | 1 High | SM | MVP | [A list of acceptance tests] | [Any thing that must be done prior to this story] | [Who asked for this feature] | [Any relevant notes] | Strategic | 1 | 1 | 1 | 4 | 4 | 4 |  |  | 0.0 MVP | 2
Unregistered User | As an unregistered user, I want to be able to register to the store, so that I can be able to be a registered user. | 1 High | 1 High | 2 Med | LG | MVP | [5 empty] | 1 | 1 | 2 | 4 | 4 | 3 |  |  | 0.0 MVP | 3
Unregistered User | As an unregistered user, I want to login to the store, so that I become a registered user or an admin. | 1 High | 1 High | 1 High | MD | MVP | [5 empty] | 1 | 1 | 1 | 4 | 4 | 4 |  |  | 0.0 MVP | 4
Unregistered User | As an unregistered user, I want to be able to explore the list of products, so that I can see their disponibility and cost. | 2 Med | 1 High | 2 Med | SM | MVP
Registered User | As a registered user, I want to be able to inspect product, so that I can explore its description and properties. | 2 Med | 2 Med | 2 Med | MD | 1.x | [5 empty] | 2 | 2 | 2 | 3 | 3 | 3 |  |  | 1.x | 6
Registered User | As a registered user, I want to be able to see my most recommended products, so that I can explore related products. | 3 Med | 2 Med | 3 Med | XLG | 2.x | [5 empty] | 3 | 2 | 3 | 2 | 3 | 2 |  |  | 2.x | 7
Registered User | As a registered user, I want to be able to add in the shopping cart a product with a quantity, so that I can buy it. | 2 Med | 2 Med | 2 Med | MD | MVP | [5 empty] | 2 | 2 | 2 | 3 | 3 | 3 |  |  | 0.0 MVP | 8
Registered User | As a registered user, I want to be able to fullfill an order, so that I can receive products at home. | 2 Med | 2 Med | 2 Med | MD | MVP | [5 empty] | 2 | 2 | 2 | 3 | 3 | 3 |  |  | 0.0 MVP | 9
Registered User | As a registered user, I want to be able to access my personal page, so that I can see the history of my orders. | 3 Med | 2 Med | 3 Med | LG | 1.x | [5 empty] | 3 | 2 | 3 | 2 | 3 | 2 |  |  | 1.x | 10
Registered User | As a registered user, I want to be able to access my personal pagea old order, so that I can see the products that I bought. | 3 Med | 2 Med | 3 Med | LG | 1.x | [5 empty] | 3 | 2 | 3 | 2 | 3 | 2 |  |  | 1.x | 11
Registered User | As a registered user, I want to be able to logout, so that I become an unregistered user. | 2 Med | 1 High | 1 High | MD | MVP | [5 empty] | 2 | 1 | 1 | 3 | 4 | 4 |  |  | 0.0 MVP | 12
Admin | As an admin, I want to add a new product, so that it can be bought. | 1 High | 1 High | 2 Med | SM | MVP | [5 empty] | 1 | 1 | 2 | 4 | 4 | 3 |  |  | 0.0 MVP | 13
Admin | As an admin, I want to be able to access statistics data, so that I can see which products are being bought the most. | 2 Med | 3 Med | 3 Med | MD | 2.x | [5 empty] | 2 | 3 | 3 | 3 | 2 | 2 |  |  | 2.x | 14
Admin | As an admin, I want to modify a product, so that I can update its availability. | 2 Med | 1 High | 1 High | MD | MVP | [5 empty] | 2 | 1 | 1 | 3 | 4 | 4 |  |  | 0.0 MVP | 15
Admin | As an admin, I want to logout, so that I become an unregistered user. | 2 Med | 1 High | 1 High | MD | MVP | [5 empty] | 2 | 1 | 1 | 3 | 4 | 4 |  |  | 0.0 MVP | 16