## Sprint 1
Sprint 1
Name |  | Project Conceptions and Documentations |  |  | (3 weeks) | 0
Goal |  | Define the Conceptions and the Documentations of the Project |  | Duration | 21
Process improvement |  | Better work estimation and projection |  | Things | 8 things
Start Date |  | 2023-07-10 |  | Task Points | 58 points
End Date |  | 2023-07-28 |  |  |  | days left
Sprint Metrics
Things Planned |  | 8 | Key Achievements | The task plan for this sprint was completed in this sprint. The Conceptions and the Documentations of the Project have been defined.
Points Planned |  | 58
Things done: |  | 8
Things left: |  | 0 | Performance Summary | The task plan requested the same hours that we planned.
Task Points done |  | 58
Task Points left: |  | 0
Sprint Backlog
Things (8) | Type | Task Points (58) | Description
Project functionalities | Task | 11 | Building the idea of the project
Research | Task | 3 | Doing research of the tools
Projections | Task | 3 | Define the projections and the workflow
Stakeholders | Task | 1 | Define the stakeholders of the project
User Stories | Task | 12 | Define the user stories of the system
Balsamiq | Task | 13 | Build the project from scratch
Function Points | Task | 8 | Fix the function points
COCOMOII | Task | 7 | Use of COCOMO Method

## Sprint 2
Sprint 2
Name |  | System Configuration |  |  | 3 weeks | 0
Goal |  | Setup the settings and the configuration of the project |  | Duration | 21
Process improvement |  | Improve commit quality |  | Things | 8 things
Start Date |  | 2023-07-31 |  | Task Points | 56 points
End Date |  | 2023-08-18 |  |  |  | days left
Sprint Metrics
Things Planned |  | 8 | Key Achievements | The task plan for this sprint was completed in this sprint. For the Referendum Idea, the implemented ideas will probably be modified in sprint 3 by implementing the further features of the project. The System Configuration and the Setting Implementation are completed.
Points Planned |  | 56
Things done: |  | 8
Things left: |  | 0 | Performance Summary | The task with title "Docker Configuration" requested more hours than the planned ones because of the problems encountered.
Task Points done |  | 56
Task Points left: |  | 0
Sprint Backlog
Things (8) | Type | Task Points (56) | Description
Maven Configuration | Task | 6 | Setup the Maven deployments
Docker Configuration | Task | 7 | Setup the JAVA User API server as a docker image
PostegreSQL Configuration | Task | 6 | Create the Web Interface Configurationand create basic preliminary GUI
RabbitMQ Configuration | Task | 8 | Setup the REST API Configuration
Web Interface Configuration | Task | 8 | Setup and configure the RabbitMQ server with web interface as a Docker image
Broadcast Configuration | Task | 9 | Create functionality to select different nation
Multiple Docker-Compose organization | Task | 4 | Create functionality to select different language
REST API Configuration | Task | 8 | Create functionality to allow registration of the user

## Sprint 3
Sprint 3
Name |  | Referendum Implementation Backend |  |  | (3 weeks) | 0
Goal |  | Implement all backend functionality |  | Duration | 21
Process improvement |  | Improve sprint reporting |  | Things | 9 things
Start Date |  | 2023-08-21 |  | Task Points | 63 points
End Date |  | 2023-09-08 |  |  |  | days left
Sprint Metrics
Things Planned |  | 9 | Key Achievements | All tasks have been completed.
Points Planned |  | 63
Things done: |  | 9
Things left: |  | 0 | Performance Summary | The consensus primitives and all the backend will be integrated with the web interface in the sprint 4
Task Points done |  | 63
Task Points left: |  | 0
Sprint Backlog
Things (9) | Type | Task Points (63) | Description
Referendum proposal functionality | Task | 5 | Create functionality to propose referendum
Referendum answer functionality | Task | 5 | Create functionality to answer referendum
Referendum display functionality | Task | 5 | Create functionality to display referendum on page
Supporting number view functionality | Task | 5 | Create functionality to display info about the referendum (number of votes)
Referendum database organization | Task | 6 | Organise the object Referendum in the database
Consensus Referendum database organization | Task | 5 | Organise the object Consensus Referendum in the database
Referendum first Consensus | Task | 14 | Build the Consensus primitive to decide if the nations want to do the Referendum
Referendum second Consensus | Task | 14 | Build the Consensus primitive to decide if the citizens agree with the Referendum
Citizens voting system | Task | 4 | Build the primitive to allow the citizens to vote

## Sprint 4
Sprint 4
Name |  | Referendum Implementation Frontend and Setting Implementation |  |  | (3 weeks) | 0
Goal |  | Implement and integrate all final functionality: graphical user interface, login and registering systems, display of informations. |  | Duration | 21
Process improvement |  | Improve sprint reporting |  | Things | 10 things
Start Date |  | 2023-08-07 |  | Task Points | 57 points
End Date |  | 2023-08-25 |  |  |  | days left
Sprint Metrics
Things Planned |  | 10 | Key Achievements | All tasks have been completed.
Points Planned |  | 57
Things done: |  | 10
Things left: |  | 0 | Performance Summary | We have integrated the Tasks of Rferendum Idea of Sprint 2 with the tasks of the Sprint 3. The time spent on integration was balanced by the less time to implement from scratch the tasks of this sprint.
Task Points done |  | 57
Task Points left: |  | 0
Sprint Backlog
Things (12) | Type | Task Points (57) | Description
Nation selection functionality | Task | 4 | Nation selection functionality
Citizen registration functionality | Task | 5 | Citizen registration functionality
Citizen authentication functionality | Task | 3 | Citizen authentication functionality
Nation representative auth functionality | Task | 4 | Nation representative auth functionality
Referendum display | Task | 5 | Referendum display
Citizens voting interface | Task | 6 | Citizens voting interface
Citizen Registration interface | Task | 5 | Citizen Registration interface
Citizen Authentication interface | Task | 6 | Citizen Authentication interface
Nation representative Auth interface | Task | 5 | Nation representative Authentication interface
Referendum proposal interface | Task | 4 | Referendum proposal interface
Referendum answer interface | Task | 5 | Referendum answer interface
Referendum results interface | Task | 5 | Referendum results interface

## Velocity
Velocity | Sprint | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 3
|  | 21 | 21 | 21 | 21
8.3333 | Planned Things | 8 | 8 | 9 | 10
59 | Planned Points | 58 | 56 | 63 | 57
8.3333 | Finished Things | 8 | 8 | 9 | 10
59 | Finished Points | 58 | 56 | 63 | 57
2.7143 | Points per dev day | 2.7619 | 2.6667 | 3 | 2.7143
100% | Commit Score | 100% | 100% | 100% | 100%