## Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
SPRINT 6
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Documentation |  | 56 | 56 | 0 |  |  |  |  | 100%
1.1 | Project Functionalities | V | 10 | 10 | 0 | 1 | 2023-09-20 | 2023-09-23 | 4 | 100% | bar: WEEK 1 W to WEEK 2 F
1.2 | User Stories | V | 10 | 10 | 0 | 1 | 2023-09-23 | 2023-09-25 | 3 | 100%
1.3 | LoFi Mockups | V | 12 | 12 | 0 | 1 | 2023-09-25 | 2023-09-29 | 5 | 100%
1.4 | Function Points Estimate | G | 8 | 8 | 0 | 1 | 2023-09-25 | 2023-09-26 | 2 | 100%
1.5 | COCOMO II | G | 7 | 7 | 0 | 1 | 2023-09-27 | 2023-09-29 | 3 | 100%
1.6 | ER schema | V | 4 | 4 | 0 | 2 | 2023-09-29 | 2023-09-29 | 1 | 100%
1.7 | Software architecture schema | V | 5 | 5 | 0 | 2 | 2023-09-30 | 2023-10-01 | 2 | 100% | bar: WEEK 2 M to WEEK 3 M
2 | System Configuration and Basic Functionalities |  | 37 | 37 | 0 |  |  |  |  | 100%
2.1 | Registration with a Google Account | G | 12 | 12 | 0 | 2 | 2023-10-01 | 2023-10-04 | 4 | 100% | bar: WEEK 2 M to WEEK 3 W
2.2 | Login | G | 6 | 6 | 0 | 2 | 2023-10-04 | 2023-10-05 | 2 | 100% | bar: WEEK 3 W to WEEK 3 R
2.3 | Logout | G | 3 | 3 | 0 | 2 | 2023-10-05 | 2023-10-05 | 1 | 100% | bar: WEEK 3 R
2.4 | Delete Account | G | 6 | 6 | 0 | 2 | 2023-10-06 | 2023-10-07 | 2 | 100% | bar: WEEK 3 F
2.5 | Profile | G | 10 | 10 | 0 | 2 | 2023-10-08 | 2023-10-10 | 3 | 100% | bar: WEEK 4 M to WEEK 4 T
3 | Development of Core Functionalities |  | 54 | 54 | 0 |  |  |  |  | 100%
3.1 | Create Calendar | G | 16 | 16 | 0 | 3 | 2023-10-11 | 2023-10-14 | 4 | 100% | bar: WEEK 4 W to WEEK 5 F
3.2 | Delete Calendar | G | 12 | 12 | 0 | 3 | 2023-10-14 | 2023-10-16 | 3 | 100%
3.3 | Search Recipes | V | 8 | 8 | 0 | 4 | 2023-10-17 | 2023-10-18 | 2 | 100%
3.4 | Show Recipes Information | V | 12 | 12 | 0 | 4 | 2023-10-18 | 2023-10-21 | 4 | 100%
3.5 | Add Event to Calendar | G | 6 | 6 | 0 | 4 | 2023-10-18 | 2023-10-19 | 2 | 100%
4 | Development of additional minor Functionalities |  | 20 | 20 | 0 |  |  |  |  | 100%
4.1 | Show Ingredient Information | V | 4 | 4 | 0 | 5 | 2023-10-22 | 2023-10-23 | 2 | 100% | bar: WEEK 5 M to WEEK 6 M
4.2 | Suggest Recipes | G | 8 | 8 | 0 | 5 | 2023-10-22 | 2023-10-24 | 3 | 100% | bar: WEEK 5 M to WEEK 6 T
4.3 | Add Recipe to Favorites | V | 4 | 4 | 0 | 5 | 2023-10-23 | 2023-10-23 | 1 | 100% | bar: WEEK 5 M to WEEK 6 M
4.4 | Remove Recipe from Favorites | V | 3 | 3 | 0 | 5 | 2023-10-24 | 2023-10-24 | 1 | 100% | bar: WEEK 6 T
4.5 | Show Favorite Recipes | V | 1 | 1 | 0 | 5 | 2023-10-24 | 2023-10-24 | 1 | 100% | bar: WEEK 6 T
5 | Finalization of the Project |  | 23 | 23 | 0 |  |  |  |  | 100%
5.1 | Mail Notification | V | 12 | 12 | 0 | 6 | 2023-10-25 | 2023-10-27 | 3 | 100% | bar: WEEK 6 W to WEEK 6 R
5.2 | GUI for Home, profile, recipes, ingredients page | V | 7 | 7 | 0 | 6 | 2023-10-27 | 2023-10-28 | 2 | 100% | bar: WEEK 6 R to WEEK 6 F
5.3 | GUI for add event to calendar and error page | G | 4 | 4 | 0 | 6 | 2023-10-27 | 2023-10-28 | 2 | 100% | bar: WEEK 6 R to WEEK 6 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 190 | 190 | 0 | 30 | 6.3333 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 190 | 183.6667 | 177.3333 | 171 | 164.6667 | 158.3333 | 152 | 145.6667 | 139.3333 | 133 | 126.6667 | 120.3333 | 114 | 107.6667 | 101.3333 | 95 | 88.6667 | 82.3333 | 76 | 69.6667 | 63.3333 | 57 | 50.6667 | 44.3333 | 38 | 31.6667 | 25.3333 | 19 | 12.6667 | 6.3333 | 0 | -6.3333 | -12.6667 | -19 | -25.3333 | -31.6667 | -38 | -44.3333 | -50.6667 | -57 | -63.3333 | -69.6667 | -76 | -82.3333 | -88.6667 | -95 | -101.3333 | -107.6667 | -114 | -120.3333 | -126.6667 | -133 | -139.3333 | -145.6667 | -152 | -158.3333 | -164.6667 | -171 | -177.3333 | -183.6667
[10 empty] | ESTIMATE | 190 | 190 | 190 | 186 | 182 | 179 | 169 | 160 | 152 | 144 | 134 | 125 | 121 | 114 | 107 | 104 | 101 | 97 | 90 | 83 | 76 | 69 | 65 | 55 | 47 | 43 | 33 | 23 | 19 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3257
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 W: 4; WEEK 1 R: 4; WEEK 1 F: 3; WEEK 2 M: 10; WEEK 2 T: 9; WEEK 2 W: 8; WEEK 2 R: 8; WEEK 2 F: 10; WEEK 3 M: 9; WEEK 3 T: 4; WEEK 3 W: 7; WEEK 3 R: 7; WEEK 3 F: 3; WEEK 4 M: 3; WEEK 4 T: 4; WEEK 4 W: 7; WEEK 4 R: 7; WEEK 4 F: 7; WEEK 5 M: 7; WEEK 5 T: 4; WEEK 5 W: 10; WEEK 5 R: 8; WEEK 5 F: 4; WEEK 6 M: 10; WEEK 6 T: 10; WEEK 6 W: 4; WEEK 6 R: 10; WEEK 6 F: 9 | 190
[10 empty] | HRS REMAINING | 190 | 190 | 186 | 182 | 179 | 169 | 160 | 152 | 144 | 134 | 125 | 121 | 114 | 107 | 104 | 101 | 97 | 90 | 83 | 76 | 69 | 65 | 55 | 47 | 43 | 33 | 23 | 19 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3067
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Project Conception and Documentation | Project Functionalities | Definition of the major functionalities of our project | V | 10 | Completed |  | Not Started | 1
High | 1 | Project Conception and Documentation | User Stories | Definition of the user stories of the system | V | 10 | Completed |  | In Progress | 2
Medium | 1 | Project Conception and Documentation | LoFi Mockups | Creation of the Low-Fidelity mockups of the the pages of our system | V | 12 | Completed |  | Completed | 3
Medium | 1 | Project Conception and Documentation | Function Points Estimate | Estimation of the function points | G | 8 | Completed |  |  | 4
Medium | 1 | Project Conception and Documentation | COCOMO II | Utilization of the COCOMO II method | G | 7 | Completed |  |  | 5
Low | 2 | Project Conception and Documentation | ER schema | Creation of the ER-schema of our system | V | 4 | Completed |  |  | 6
Low | 2 | Project Conception and Documentation | Software architecture schema | Creation of the schema of our system's architecture | V | 5 | Completed |  |  | 7
High | 2 | System Configuration and Basic Functionalities | Registration with a Google Account | Creation of the functionality to register with a Google account in our system | G | 12 | Completed |  |  | 8
Medium | 2 | System Configuration and Basic Functionalities | Login | Creation of the functionality to login in our system | G | 6 | Completed |  |  | 9
Medium | 2 | System Configuration and Basic Functionalities | Logout | Creation of the functionality to logout from our system | G | 3 | Completed |  |  | 10
Medium | 2 | System Configuration and Basic Functionalities | Delete Account | Managing the deletion of an account from the system | G | 6 | Completed |  |  | 11
High | 2 | System Configuration and Basic Functionalities | Profile | Managing the information to be shown in the user profile | G | 10 | Completed |  |  | 12
Medium | 3 | Development of Core Functionalities | Create Calendar | Creation of the functionality to create a Calendar directly in our system | G | 16 | Completed |  |  | 13
Medium | 3 | Development of Core Functionalities | Delete Calendar | Creation of the functionality to delete a Calendar directly in our system | G | 12 | Completed |  |  | 14
Medium | 4 | Development of Core Functionalities | Search Recipes | Creation of the functionality to search for recipes by name with an external API | V | 8 | Completed |  |  | 15
Medium | 4 | Development of Core Functionalities | Show Recipes Information | Creation of the functionality to get the information for recipes with an external API | V | 12 | Completed |  |  | 16
High | 4 | Development of Core Functionalities | Add Event to Calendar | Creation of the functionality to add an event to a Calendar directly in our system | G | 6 | Completed
Low | 5 | Development of additional minor Functionalities | Show Ingredient Information | Creation of the functionality to get the information for ingredients with an external API | V | 4 | Completed
Medium | 5 | Development of additional minor Functionalities | Suggest Recipes | Creation of the functionality to get the suggested recipes for a specific diet with a Chat-BOT | G | 8 | Completed
Medium | 5 | Development of additional minor Functionalities | Add Recipe to Favorites | Creation of the functionality to add recipes to a favorite list | V | 4 | Completed
Low | 5 | Development of additional minor Functionalities | Remove Recipe from Favorites | Creation of the functionality to delete recipes from the favorite list | V | 3 | Completed
Medium | 5 | Development of additional minor Functionalities | Show Favorite Recipes | Creation of the functionality to show all the recipes of the favorite list in the user profile | V | 1 | Completed
Medium | 6 | Finalization of the Project | Mail Notification | Creation of the functionality to send an email to the Google account used during registration | V | 12 | Completed
Low | 6 | Finalization of the Project | GUI for Home, profile, recipes, ingredients page | Improved the GUI for the Home, profile, recipes and ingredients pages | V | 7 | Completed
Low | 6 | Finalization of the Project | GUI for add event to calendar and error page | Improved the GUI for the add event to calendar and error pages | G | 4 | Completed