## Sprint 1
Sprint 1
Name |  | Initial Sprint |  |  |  | 0
Goal |  | Define basic functionalities and documentation |  | Duration | 8 working days
Process improvement |  | Improve the estimation of the work |  | Things | 5 things
Start Date |  | 2023-09-20 |  | Story Points | 47 points
End Date |  | 2023-09-29 |  |  |  | days left
Sprint Metrics
Things Planned |  | 5 | Key Achievements | The task plan for this sprint was correctly completed. The general conceptions and the documentations of the Project have been defined.
Points Planned |  | 47
Things done: |  | 5
Things left: |  | 0 | Performance Summary | The tasks we identified requested the same amount of hours we initially planned.
Story Points done |  | 47
Story Points left: |  | 0
Sprint Backlog
Things (5) | Type | Story Points (47) | Description
Project Functionalities | task | 10 | Definition of the major functionalities of our project
User Stories | task | 10 | Definition of the user stories of the system
LoFi Mockups | task | 12 | Creation of the Low-Fidelity mockups of the the pages of our system
Function Points Estimate | task | 8 | Estimation of the function points
COCOMO II | task | 7 | Utilization of the COCOMO II method

## Sprint 2
Sprint 2
Name |  | Second Sprint |  |  |  | 0
Goal |  | System Configuration and Basic Functionalities |  | Duration | 8 working days
Process improvement |  | Improve the commit quality |  | Things | 7 things
Start Date |  | 2023-09-29 |  | Story Points | 46 points
End Date |  | 2023-10-10 |  |  |  | days left
Sprint Metrics
Things Planned |  | 7 | Key Achievements | In this sprint we successfully delivered a first working version of the system, with basic functionalities as the registration in the website.
Points Planned |  | 46
Things done: |  | 7
Things left: |  | 0 | Performance Summary | Similarly to the first sprint, we managed to complete everything we had planned in the identified estimated days. The amount of work was similar to that of the first sprint
Story Points done |  | 46
Story Points left: |  | 0
Sprint Backlog
Things (7) | Type | Story Points (46) | Description
ER schema | task | 4 | Creation of the ER-schema of our system
Software architecture schema | task | 5 | Creation of the schema of our system's architecture
Registration with a Google Account | story | 12 | Creation of the functionality to register with a Google account in our system
Login | story | 6 | Creation of the functionality to login in our system
Logout | story | 3 | Creation of the functionality to logout from our system
Delete Account | story | 6 | Managing the deletion of an account from the system
Profile | story | 10 | Managing the information to be shown in the user profile

## Sprint 3
Sprint 3
Name |  | Third Sprint |  |  |  | 0
Goal |  | First set of Core functionalities |  | Duration | 4 working days
Process improvement |  | Improve the coding quality |  | Things | 2 things
Start Date |  | 2023-10-11 |  | Story Points | 28 points
End Date |  | 2023-10-16 |  |  |  | days left
Sprint Metrics
Things Planned |  | 2 | Key Achievements | The first set of core functionalities has been implemented, while also assuring a general robustness to the working system.
Points Planned |  | 28
Things done: |  | 2
Things left: |  | 0 | Performance Summary | For this sprint, only one of the two team members could work on the project, as to why only two major "things" have been developed.
Story Points done |  | 28
Story Points left: |  | 0
Sprint Backlog
Things (2) | Type | Story Points (28) | Description
Create Calendar | story | 16 | Creation of the functionality to create a Calendar directly in our system
Delete Calendar | story | 12 | Creation of the functionality to delete a Calendar directly in our system

## Sprint 4
Sprint 4
Name |  | Fourth Sprint |  |  |  | 0
Goal |  | Second set of Core functionalities |  | Duration | 4 working days
Process improvement |  | Improve sprint reporting |  | Things | 3 things
Start Date |  | 2023-10-17 |  | Story Points | 26 points
End Date |  | 2023-10-21 |  |  |  | days left
Sprint Metrics
Things Planned |  | 3 | Key Achievements | The second set of core functionalities has been implemented into the system, and additional improvements were brought for existing functionalities.
Points Planned |  | 26
Things done: |  | 3
Things left: |  | 0 | Performance Summary | Nothing particularly interesting to report.
Story Points done |  | 26
Story Points left: |  | 0
Sprint Backlog
Things (3) | Type | Story Points (26) | Description
Search Recipes | story | 8 | Creation of the functionality to search for recipes by name with an external API
Show Recipes Information | story | 12 | Creation of the functionality to get the information for recipes with an external API
Add Event to Calendar | story | 6 | Creation of the functionality to add an event to a Calendar directly in our system

## Sprint 5
Sprint 5
Name |  | Fifth Sprint |  |  |  | 0
Goal |  | Additional minor functionalities |  | Duration | 2 working days
Process improvement |  | Improve sprint reporting and team synergy |  | Things | 5 things
Start Date |  | 2023-10-22 |  | Story Points | 20 points
End Date |  | 2023-10-24 |  |  |  | days left
Sprint Metrics
Things Planned |  | 5 | Key Achievements | Other minor functionalities have been successfully implemented in the system.
Points Planned |  | 20
Things done: |  | 5
Things left: |  | 0 | Performance Summary | For this sprint, the team had to pursue an additional effort to implement all the planned functionalities.
Story Points done |  | 20
Story Points left: |  | 0
Sprint Backlog
Things (5) | Type | Story Points (20) | Description
Show Ingredient Information | story | 4 | Creation of the functionality to get the information for ingredients with an external API
Suggest Recipes | story | 8 | Creation of the functionality to get the suggested recipes for a specific diet with a Chat-BOT
Add Recipe to Favorite | story | 4 | Creation of the functionality to add recipes to a favorite list
Remove Recipe from Favorites | story | 3 | Creation of the functionality to delete recipes from the favorite list
Show Favorite Recipes | story | 1 | Creation of the functionality to show all the recipes of the favorite list in the user profile

## Sprint 6
Sprint 6
Name |  | Sixth Sprint |  |  |  | 0
Goal |  | Last functionalities and polishing of the GUI |  | Duration | 3 working days
Process improvement |  | Improve the overall code integration |  | Things | 3 things
Start Date |  | 2023-10-25 |  | Story Points | 23 points
End Date |  | 2023-10-28 |  |  |  | days left
Sprint Metrics
Things Planned |  | 3 | Key Achievements | In this sprint we focused on the last aspects of the project, including the polishment of the GUI of the pages. We successfully concluded all the planned activities for the project.
Points Planned |  | 23
Things done: |  | 3
Things left: |  | 0 | Performance Summary | In this last sprint the team managed to successfully complete all the "things" in the estimated time.
Story Points done |  | 23
Story Points left: |  | 0
Sprint Backlog
Things (3) | Type | Story Points (23) | Description
Mail Notification | story | 12 | Creation of the functionality to send an email to the Google account used during registration
GUI for Home, profile, recipes, ingredients page | improvement | 7 | Improved the GUI for the Home, profile, recipes and ingredients pages
GUI for add event to calendar and error page | improvement | 4 | Improved the GUI for the add event to calendar and error pages

## Velocity
Velocity | Sprint | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7
| Working Days | 8 | 8 | 4 | 4 | 2 | 3
4.1667 | Planned Things | 5 | 7 | 2 | 3 | 5 | 3
31.6667 | Planned Points | 47 | 46 | 28 | 26 | 20 | 23
4.1667 | Finished Things | 5 | 7 | 2 | 3 | 5 | 3
31.6667 | Finished Points | 47 | 46 | 28 | 26 | 20 | 23
7.1319 | Points per dev day | 5.875 | 5.75 | 7 | 6.5 | 10 | 7.6667
100% | Commit Score | 100% | 100% | 100% | 100% | 100% | 100%