## User Stories
EPIC | USER STORY | PRIORITY | VALUE | RISK | ESTIMATE | RELEASE | ACCEPTANCE | DEPENDENCIES | REQUESTOR | NOTES | VALUE/RISK MATRIX | PRIORITY(INT) | VALUE(INT) | RISK(INT) | PRIORITY(INV) | VALUE(INV) | RISK(INV) | THEME(Sp) | FEATURE(Sp) | RELEASE(S) | ROW(S)
Registration | As a visitor, I want to be able to register in the website with an external account, so that I can use an existing Google account | 1 High | 1 High | 2 Med | LG | 1.x | Upon registering, the user will automatically be logged in the website, with the navbar reflecting the change by showing the updated info | Possession of a Google account | [Who asked for this feature] | The user must accept Google Terms of Service and agree with the use of Google Calendar if he wants to interact with it directly in the website | Strategic | 1 | 1 | 2 | 4 | 4 | 3 |  |  | 1.x | 2
Search recipes | As a visitor, I want to be able to search a recipe by its name, so that I can search only what interests me | 2 Med | 2 Med | 3 Med | MD | 3.x | The user will see a list of recipes matching the searched value | API service provider and related API Key |  | The user must avoid being too specific in the search terms since most recipes are particularly specific in their names |  | 2 | 2 | 3 | 3 | 3 | 2 |  |  | 3.x | 3
Show Recipe Information | As a visitor, I want to be able to see the information of a recipe, so that I can learn more about it | 2 Med | 1 High | 3 Med | LG | 3.x | The user will have specific information about the selected recipe, in the form of extended description of ingredients, instructions ecc | Depends on the user story in row #3 |  | The user should notice that each ingredient's card is interactive |  | 2 | 1 | 3 | 3 | 4 | 2 |  |  | 3.x | 4
Show Ingredient Information | As a visitor, I want to be able to see the information of an ingredient, so that I can know the details of each ingredient in a recipe | 4 Low | 3 Med | 4 Low | SM | 4.x | The user will see extended information about the selected ingredient | Depends on the user story in row #4 |  |  |  | 4 | 3 | 4 | 1 | 2 | 1 |  |  | 4.x | 5
Suggest Recipes | As a visitor, I want to be able to check the suggested recipes for a specific diet, so that I can be inspired in what to prepare each day | 3 Med | 2 Med | 2 Med | LG | 4.x | The user will receive messages from the Chat-BOT in an asynchronous way | API service provider and related API Key |  |  |  | 3 | 2 | 2 | 2 | 3 | 3 |  |  | 4.x | 6
Login | As a registered user, I want to be able to perform the login, so that I can access other system's functionalities | 2 Med | 1 High | 2 Med | MD | 1.x | The user will notice the change in the navbar reflecting that he is logged in the website | Depends on the user story in row #2 |  |  |  | 2 | 1 | 2 | 3 | 4 | 3 |  |  | 1.x | 7
Logout | As a registered user, I want to be able to perform the logout, so that I can leave my information within the website | 3 Med | 3 Med | 4 Low | SM | 1.x | The user will be redirected to the home page, noticing the possibility to login | Depends on the user story in row #7
Profile | As a registered user, I want to be able to access my profile page, so that I can check my personal information | 1 High | 1 High | 2 Med | LG | 1.x | The user will see all of his information in a detailed page, including his account data as well as his favorites recipes and his calendar | Depends on the user story in row #2 and #7 |  | After the first registration, this page may be relatively empty so it is suggested that the user interacts a little bit with the system first |  | 1 | 1 | 2 | 4 | 4 | 3 |  |  | 1.x | 9
Calendar Creation | As a registered user, I want to be able to create a Calendar, so that I can populate it with events relating recipes | 2 Med | 2 Med | 1 High | XLG | 2.x | Upon clicking the add button, the user will see the newly created calendar in the profile page | Depends on the user story in row #2 and #7 |  | Since a number of API calls to the Google Calendar API needs to be done, as well as an interaction with the database, a small amount of time is needed in order to correctly visualize the calendar in the profile page |  | 2 | 2 | 1 | 3 | 3 | 4 |  |  | 2.x | 10
Calendar Deletion | As a registered user, I want to be able to delete a Calendar, so that I can remove the data gathered within the website | 3 Med | 3 Med | 4 Low | LG | 2.x | Upon clicking the delete button, the user will notice that the calendar will no longer be visible in the profile page | Depends on the user story in row #10 |  | As before, a small amount of time may be needed in order to properly update the profile page |  | 3 | 3 | 4 | 2 | 2 | 1 |  |  | 2.x | 11
Add Event | As a registered user, I want to be able to add an event to my Calendar, so that I can be reminded on a specific day to prepare a particular recipe | 1 High | 2 Med | 3 Med | MD | 3.x | After filling the required form information, the user will be redirected to his profile page and see the newly added event | Depends on the user story in row #10 and #4 |  | If the event is added for days not displayed in the current month, the user needs to scroll the various months of the calendar to check the new event |  | 1 | 2 | 3 | 4 | 3 | 2 |  |  | 3.x | 12
Add Recipe to Favorites | As a registered user, I want to be able to add a recipe to my favorite list, so that I can keep track of all the recipes I like | 2 Med | 1 High | 3 Med | MD | 4.x | When the user is logged in, after clicking on the button to add the current recipe to his favorite list, he can see his list updated correctly in his profile | Depends on the user story in row #7 and #4 |  | In order to provide the best navigation for the user, after he adds a recipe to his favorite list, he will not automatically be redirected to the profile, remaining at the current visited page |  | 2 | 1 | 3 | 3 | 4 | 2 |  |  | 4.x | 13
Remove Recipe from Favorites | As a registered user, I want to be able to remove a recipe from my favorite list, so that I can stop being interested in it | 4 Low | 3 Med | 4 Low | MD | 4.x | The user will see his favorite list automatically updated in his profile, with the selected recipe removed from the list | Depends on the user story in row #9 |  | It follows the same principles of the previous user story |  | 4 | 3 | 4 | 1 | 2 | 1 |  |  | 4.x | 14
Show Favorites List | As a registered user, I want to be able to see my favorite list, so that I can check my current interests in recipes | 2 Med | 1 High | 2 Med | SM | 4.x | Once entering the profile, the user will be able to correctly see the displayed favorite list, at the right-hand side of the page | Depends on the user story in row #9 |  |  |  | 2 | 1 | 2 | 3 | 4 | 3 |  |  | 4.x | 15
Delete Account | As a registered user, I want to be able to delete my personal account, so that I can remove everything related to it from the website | 2 Med | 2 Med | 2 Med | MD | 1.x | The user will automatically be redirected to the home page, in which he has the ability to register to the website again | Depends on the user story in row #9 |  | When deleting the account from the website, the user will not be automatically have the consent removed from the services he agreed before (Google account and Google Calendar). In order to do so, he has to enter his personal area in his Google account and remove the consents manually |  | 2 | 2 | 2 | 3 | 3 | 3 |  |  | 1.x | 16
Mail Notification | As a visitor, I want to be able to receive a mail notification when registering, so that I can know if the registration process has succeeded | 2 Med | 3 Med | 2 Med | LG | 5.x | The user will receive a mail to the Google account used to register in the system | Depends on the user story in row #2 |  | The user may not have the notifications activated for gmail, so in order to see the feedback he may directly enter the app and check the latest mails |  | 2 | 3 | 2 | 3 | 2 | 3 |  |  | 5.x | 17