## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT ONE SPORT CHART
ONE SPORT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Setup of the environment |  | 60 | 60 | 120 |  |  |  | 12 | 100%
1.1 | Database + containerization of DB | Valerio | 10 | 10 | 0 | 1 | 2023-06-19 | 2023-06-20 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T
1.2 | Setup of preliminary containers | Eugenio | 10 | 10 | 0 | 1 | 2023-06-19 | 2023-06-20 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T
1.3 | Connecting all the preliminary microservices | Sasanelli | 15 | 15 | 0 | 1 | 2023-06-21 | 2023-06-23 | 3 | 100% | bar: WEEK 1 W to WEEK 2 F
1.4 | React Setup | Sudoso | 15 | 15 | 0 | 1 | 2023-06-26 | 2023-06-28 | 3 | 100%
1.5 | Login + Logout setup | Sudoso | 10 | 10 | 0 | 1 | 2023-06-29 | 2023-06-30 | 2 | 100%
2 | Backend development |  | 50 | 50 | 100 |  |  |  | 9 | 100%
2.1 | Authentication Microservice | Andrea | 10 | 10 | 0 | 2 | 2023-07-03 | 2023-07-04 | 2 | 100% | bar: WEEK 2 M to WEEK 3 T
2.2 | Ticket Microservice | Valerio | 10 | 10 | 0 | 2 | 2023-07-05 | 2023-07-06 | 2 | 100% | bar: WEEK 3 W to WEEK 3 T
2.3 | Friends Microservice | Sasanelli | 10 | 10 | 0 | 2 | 2023-07-06 | 2023-07-07 | 2 | 100% | bar: WEEK 3 T to WEEK 3 F
2.4 | News Microservice | Andrea | 15 | 15 | 0 | 2 | 2023-07-10 | 2023-07-12 | 3 | 100% | bar: WEEK 4 M to WEEK 4 W
2.5 | Testing the backend | Eugenio | 5 | 5 | 0 | 2 | 2023-07-13 | 2023-07-14 | 2 | 100% | bar: WEEK 4 T to WEEK 5 F
3 | Frontend development |  | 65 | 65 | 130 |  |  |  | 17 | 100%
3.1 | Homepage setup | Sasanelli | 15 | 15 | 0 | 3 | 2023-07-17 | 2023-07-18 | 2 | 100%
3.2 | Add news API + Filter System | Andrea | 10 | 10 | 0 | 3 | 2023-07-19 | 2023-07-20 | 2 | 100%
3.3 | Add Ticket API + Filter system | Eugenio | 15 | 15 | 0 | 3 | 2023-07-20 | 2023-07-21 | 2 | 100%
3.4 | Friend Page | Andrea | 10 | 10 | 0 | 3 | 2023-07-24 | 2023-07-25 | 2 | 100% | bar: WEEK 5 M to WEEK 6 T
3.5 | Responsive Frontend | Sudoso | 15 | 15 | 0 | 3 | 2023-07-26 | 2023-07-28 | 3 | 100% | bar: WEEK 6 W to WEEK 6 F
4 | Finalization of functionalities and testing |  | 38 | 38 | 76 |  |  |  | 13 | 100%
4.1 | Testing of Authentication API | Valerio | 10 | 10 | 0 | 4 | 2023-09-04 | 2023-09-06 | 3 | 100%
4.2 | Testing of News API | Eugenio | 10 | 10 | 0 | 4 | 2023-09-06 | 2023-09-08 | 3 | 100%
4.3 | Testing of ticket API | Sudoso | 3 | 3 | 0 | 4 | 2023-09-11 | 2023-09-12 | 2 | 100% | bar: WEEK 11 M to WEEK 12 T
4.4 | Testing of Friends API | Valerio | 15 | 15 | 0 | 4 | 2023-09-13 | 2023-09-15 | 3 | 100% | bar: WEEK 12 W to WEEK 12 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS worked in total (if we worked the same day we count it as 1 day) | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 754 | 754 | 230 | 66 | 11.4242 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | [10 empty] | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 754 | 754 | 754 | 754 | 742.5758 | 731.1515 | 719.7273 | 708.303 | 696.8788 | 685.4545 | 674.0303 | 662.6061 | 651.1818 | 639.7576 | 628.3333 | 616.9091 | 605.4848 | 594.0606 | 582.6364 | 571.2121 | 559.7879 | 548.3636 | 536.9394 | 525.5152 | 514.0909 | 502.6667 | 491.2424 | 479.8182 | 468.3939 | 456.9697 | 445.5455 | 434.1212 | 422.697 | 411.2727 | 399.8485 | 388.4242 | 377 | 365.5758 | 354.1515 | 342.7273 | 331.303 | 319.8788 | 308.4545 | 297.0303 | 285.6061 | 274.1818 | 262.7576 | 251.3333 | 239.9091 | 228.4848
[10 empty] | ESTIMATE | 754 | 751 | 748 | 754 | 749 | 744 | 741 | 738 | 735 | 729 | 726 | 722 | 716 | 709 | 704 | 699 | 694 | 689 | 684 | 681 | 678 | 675 | 671 | 668 | 664 | 660 | 657 | 654 | 651 | 648 | 645 | 641 | 637 | 633 | 629 | 621 | 614 | 610 | 606 | 602 | 599 | 599 | 599 | 599 | 599 | 599 | 599 | 599 | 599 | 599 | [10 empty] | 31068
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 6 | 3 | 4 | 6 | 7 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 8 | 7 | 4 | 4 | 4 | 3 | [20 empty] | 155
[10 empty] | HRS REMAINING | 751 | 748 | 745 | 749 | 744 | 741 | 738 | 735 | 729 | 726 | 722 | 716 | 709 | 704 | 699 | 694 | 689 | 684 | 681 | 678 | 675 | 671 | 668 | 664 | 660 | 657 | 654 | 651 | 648 | 645 | 641 | 637 | 633 | 629 | 621 | 614 | 610 | 606 | 602 | 599 | 599 | 599 | 599 | 599 | 599 | 599 | 599 | 599 | 599 | 599 | [10 empty] | 30913
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Having the whole environment ready | Setup of the Environment | In this sprint our objective was to have all the basics structure implemented |  | 40 | Completed |  | Not Started | 1
High | 2 | Implementing the backend functionalities | Backend Development | We exclusively focused on the microservices' backend, diligently working on and thoroughly testing all the endpoints using Testfully. |  | 40 | Completed |  | In Progress | 2
High | 3 | Implementing the frontend functionalities | Frontend Development | We utilized React to establish the connection between the Backend and Frontend, as well as to build the initial set of features. |  | 80 | Completed |  | Completed | 4
Medium | 4 | Finalization of the system | Finalization and testing | Execution of the final features, comprehensive testing of both the features and the fully deployed system. |  | 40 | Completed |  |  | 8
16
24
40
80