## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Homepage First |  | 31 | 31 | 0 |  |  |  |  | 100%
1.1 | Display treemap with stocks information | Elena | 10 | 10 | 0 | 1 | 2023-03-15 | 2023-03-17 | 3 | 100% | bar: WEEK 1 W to WEEK 2 F
1.2 | Display sliding view of main tickers | Elena | 8.5 | 8.5 | 0 | 1 | 2023-03-17 | 2023-03-22 | 4 | 100% | bar: WEEK 1 F to WEEK 2 F
1.3 | Display the hottest sector in the market | Elena | 5.5 | 5.5 | 0 | 1 | 2023-03-22 | 2023-03-27 | 4 | 100% | bar: WEEK 2 M to WEEK 3 M
1.4 | Display sorted list of biggest gainers and losers | Elena | 7 | 7 | 0 | 1 | 2023-03-27 | 2023-03-31 | 5 | 100% | bar: WEEK 2 M to WEEK 3 F
2 | Homepage Second |  | 30 | 30 | 0 |  |  |  |  | 100%
2.1 | Display the page loading | Elena | 3 | 3 | 0 | 2 | 2023-03-31 | 2023-04-03 | 2 | 100% | bar: WEEK 3 F to WEEK 4 M
2.2 | Display information about main index | Elena | 10 | 10 | 0 | 2 | 2023-04-04 | 2023-04-14 | 9 | 100% | bar: WEEK 4 T to WEEK 5 F
2.3 | Display market news | Elena | 9 | 9 | 0 | 2 | 2023-04-14 | 2023-04-21 | 6 | 100% | bar: WEEK 5 M to WEEK 6 F
2.4 | Navigate to news website | Tiziano | 8 | 8 | 0 | 2 | 2023-04-25 | 2023-04-28 | 4 | 100% | bar: WEEK 6 T to WEEK 6 F
3 | Account |  | 52 | 52 | 0 |  |  |  |  | 100%
3.1 | Register Account | Andrea | 15 | 15 | 0 | 3 | 2023-04-26 | 2023-05-03 | 6 | 100% | bar: WEEK 6 W to WEEK 7 W
3.2 | Login to Account | Andrea | 15 | 15 | 0 | 3 | 2023-05-03 | 2023-05-10 | 6 | 100% | bar: WEEK 7 W to WEEK 8 F
3.3 | Logout | Andrea | 6 | 6 | 0 | 3 | 2023-05-10 | 2023-05-15 | 4 | 100% | bar: WEEK 8 M to WEEK 9 M
3.4 | Delete Account | Andrea | 8 | 8 | 0 | 3 | 2023-05-15 | 2023-05-17 | 3 | 100% | bar: WEEK 8 M to WEEK 9 W
3.5 | Customize Account | Andrea | 8 | 8 | 0 | 3 | 2023-05-17 | 2023-05-19 | 3 | 100% | bar: WEEK 9 W to WEEK 9 F
4 | Cryptocurrencies |  | 28 | 28 | 0 |  |  |  |  | 100%
4.1 | Display cryptos info in a treemap | Elena | 10 | 10 | 0 | 4 | 2023-05-17 | 2023-05-22 | 4 | 100% | bar: WEEK 9 W to WEEK 10 M
4.2 | Get information about trending cryptos | Elena | 9 | 9 | 0 | 4 | 2023-05-23 | 2023-05-29 | 5 | 100% | bar: WEEK 10 T to WEEK 11 F
4.3 | Get information about most famous cryptos | Elena | 9 | 9 | 0 | 4 | 2023-05-29 | 2023-06-01 | 4 | 100%
5 | Search and Favorites |  | 18 | 18 | 0 |  |  |  |  | 100%
5.1 | Search for specific stocks | Tiziano | 10 | 10 | 0 | 5 | 2023-05-31 | 2023-06-02 | 3 | 100%
5.2 | Display information about specific stock | Tiziano | 8 | 8 | 0 | 5 | 2023-06-02 | 2023-06-05 | 2 | 100% | bar: WEEK 11 M to WEEK 12 M
5.3 | Save favorite stocks | Tiziano | 8 | 8 | 0 | 5 | 2023-06-05 | 2023-06-07 | 3 | 100% | bar: WEEK 11 M to WEEK 12 W
5.4 | Show favorite stocks | Andrea | 7 | 7 | 0 | 5 | 2023-06-06 | 2023-06-08 | 3 | 100% | bar: WEEK 12 T to WEEK 12 R
5.5 | Delete favorite stocks | Andrea | 6 | 6 | 0 | 5 | 2023-06-08 | 2023-06-09 | 2 | 100% | bar: WEEK 12 R to WEEK 12 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 180 | 180 | 0 | 60 | 3 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 180 | 177 | 174 | 171 | 168 | 165 | 162 | 159 | 156 | 153 | 150 | 147 | 144 | 141 | 138 | 135 | 132 | 129 | 126 | 123 | 120 | 117 | 114 | 111 | 108 | 105 | 102 | 99 | 96 | 93 | 90 | 87 | 84 | 81 | 78 | 75 | 72 | 69 | 66 | 63 | 60 | 57 | 54 | 51 | 48 | 45 | 42 | 39 | 36 | 33 | 30 | 27 | 24 | 21 | 18 | 15 | 12 | 9 | 6 | 3
[10 empty] | ESTIMATE | 180 | 180 | 180 | 174 | 172 | 169 | 166 | 163 | 161 | 159 | 157 | 154 | 153 | 152 | 151 | 148 | 147 | 145 | 144 | 143 | 142 | 141 | 140 | 139 | 138 | 136 | 132 | 127 | 121 | 115 | 110 | 107 | 104 | 103 | 100 | 98 | 95 | 92 | 88 | 86 | 84 | 79 | 76 | 70 | 66 | 61 | 57 | 55 | 53 | 51 | 49 | 45 | 41 | 36 | 31 | 22 | 16 | 12 | 7 | 4 | 6427
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 0 | 0 | 6 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 5 | 6 | 6 | 5 | 3 | 3 | 1 | 3 | 2 | 3 | 3 | 4 | 2 | 2 | 5 | 3 | 6 | 4 | 5 | 4 | 2 | 2 | 2 | 2 | 4 | 4 | 5 | 5 | 9 | 6 | 4 | 5 | 3 | 4 | 180
[10 empty] | HRS REMAINING | 180 | 180 | 174 | 172 | 169 | 166 | 163 | 161 | 159 | 157 | 154 | 153 | 152 | 151 | 148 | 147 | 145 | 144 | 143 | 142 | 141 | 140 | 139 | 138 | 136 | 132 | 127 | 121 | 115 | 110 | 107 | 104 | 103 | 100 | 98 | 95 | 92 | 88 | 86 | 84 | 79 | 76 | 70 | 66 | 61 | 57 | 55 | 53 | 51 | 49 | 45 | 41 | 36 | 31 | 22 | 16 | 12 | 7 | 4 | 0 | 6247

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Display the main stocks' information in the homepage | Homepage First | The main claim of this sprint is to display a treemap with the main stocks of different sectors, two lists, one with the bigger gainers and the other one with the worse losers, the horizontal scrolling of the tickers and their percentage changes, and three boxes with different information such as the biggest gainer, the worst loser, and the hottest sector. | Elena | 40 | Completed | This would be the starting point of the application, with the main features that we want to display | Not Started | 1
Med | 2 | Show more information in the homepage | Homepage Second | The claim of this sprint is to add a box on the top of the homepage, in which there is shown the latest best index, and also a box of the latest news about the stock market. | Elena and Tiziano | 24 | Completed | With this sprint, the homepage is finished | In Progress | 2
High | 3 | Create and manage an account | Account | The goal of this sprint is to add the possility to create an account, log in and log out in the application, to customize and delete the account | Andrea | 40 | Completed | Also security has been managed | Completed | 4
Med | 4 | Creation of another page with cryptocurrencies' information | Cryptocurrencies | The main claim of this sprint is to create a new page with information about cryptocurrencies, with two lists, one of the most trending cryptos and the other with the most famous ones.The page must have also a treemap of all the cryptocurrencies. | Elena | 24 | Completed | This sprint allows to create a more detailed finance web application |  | 8
High | 5 | Search for the stocks' trending and add stocks to a list of favorite | Search and Favorites | With this sprint, it is possible to search for the wanted ticker, from the homepage, and navigated through the results, it is displayed a candle stick graph of such stock with other information. It is also possible to add and remove such stocks into a list of favorite ones. | Tiziano and Andrea | 16 | Completed | This sprint allows to realize a more customize usage of the application |  | 16
24
40
80

## Product Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Homepage First | Display a treemap with stocks information | Plot in a treemap the information of the main stocks per each sector managing the communication between Spring Boot and Nodejs through RabbitMQ, and realizing some API request to Finnhub from the Nodejs container | Elena | 16 | Completed | Not Started | 1
High | 1 | Homepage First | Display sliding view of main tickers | Display the percentage change of the main stocks managing the communication between Spring Boot and Nodejs through RabbitMQ, and realizing some API request to Finnhub from the Nodejs container | Elena | 8 | Completed | In Progress | 2
High | 1 | Homepage First | Display the hottest sector in the market | Display the hottest secot in the market managing the communication between Spring Boot and Nodejs through RabbitMQ, and realizing some API request to Finnhub from the Nodejs container | Elena | 8 | Completed | Completed | 4
High | 1 | Homepage First | Display sorted list of biggest gainers and losers | Display a sorted list of biggest gainers and the one of the biggest losers managing the communication between Spring Boot and Nodejs through RabbitMQ, and realizing some API request to Finnhub from the Nodejs container | Elena | 8 | Completed |  | 8
Med | 2 | Homepage Second | Display the page loading | Display a loader after each interaction with the application | Elena | 4 | Completed |  | 16
High | 2 | Homepage Second | Display information about main index | Display the information of the la main index managing the communication between Spring Boot and Nodejs through RabbitMQ, and realizing some API request to Finnhub from the Nodejs container | Elena | 16 | Completed |  | 24
Med | 2 | Homepage Second | Display market news | Display the latest market news managing the communication between Spring Boot and Nodejs through RabbitMQ, and realizing some API request to Finnhub from the Nodejs container | Elena | 8 | Completed |  | 40
Med | 2 | Homepage Second | Navigate to news website | Allow to navigate to the news website through each news title dispalyed | Tiziano | 8 | Completed |  | 80
High | 3 | Account | Register Account | Save in the database the information of a new user | Andrea | 16 | Completed
High | 3 | Account | Login to Account | Allow to use the application thorugh his own account through a session cookie | Andrea | 16 | Completed
High | 3 | Account | Logout | Remove the session cookie | Andrea | 8 | Completed
Med | 3 | Account | Delete Account | Remove the account from the database | Andrea | 8 | Completed
Low | 3 | Account | Customize Account | Allow the user to update his information in the database | Andrea | 8 | Completed
Med | 4 | Cryptocurrencies | Display cryptos info in a treemap | Plot in a treemap the information of the main cryptos the communication between Spring Boot and Nodejs through RabbitMQ, and realizing some API request to Finnhub from the Nodejs container | Elena | 16 | Completed
Med | 4 | Cryptocurrencies | Get information about trending cryptos | Display theinformation sorting on the percentage change of the main cryptocurrencies managing the communication between Spring Boot and Nodejs through RabbitMQ, and realizing some API request to CoinMarketCap from the Nodejs container | Elena | 8 | Completed
Med | 4 | Cryptocurrencies | Get information about most famous cryptos | Display theinformation sorting on the number of coin in circulation of the main cryptocurrencies managing the communication between Spring Boot and Nodejs through RabbitMQ, and realizing some API request to CoinMarketCap from the Nodejs container | Elena | 8 | Completed
High | 5 | Search and favorites | Search for specific stocks | Realize a POST request with some information, managing the communication between Spring Boot and Nodejs through RabbitMQ, and realizing some API request to Finnhub from the Nodejs container | Tiziano | 16 | Completed
High | 5 | Search and favorites | Display information about specific stock | Plot a candlestick graph and other information about a certain stock, managing the communication between Spring Boot and Nodejs through RabbitMQ, and realizing some API request to Finnhub from the Nodejs container | Tiziano | 8 | Completed
Med | 5 | Search and favorites | Save favorite stocks | Update the list of favorite stocks of the current user into the database | Tiziano | 8 | Completed
Med | 5 | Search and favorites | Show favorite stocks | Get the list of favorite stocks of the current user from the database | Andrea | 8 | Completed
Med | 5 | Search and favorites | Delete favorite stocks | Update the list of favorite stocks of the current user into the database | Andrea | 8 | Completed