## Copia di SCRUM Template - Sprin
PB Name | Task Name | Description and details | Check Out | Status | Remaining Effort [hr] | Day
[5 empty] | 80 | 1
Sprint Backlog | Backend | Analyse dataset | Ahmed | Doing | 70 | 2
Sprint Backlog | Backend | dataset extract features | Ahmed | Doing | 65 | 3
Sprint Backlog | Backend | create inferer Service | Ahmed | Doing | 50 | 4
Sprint Backlog | Backend | create auth service | Ahmed | Doing | 40 | 5
Sprint Backlog | Backend | create emulator service | Ernest | Doing | 30 | 6
Sprint Backlog | Backend | analyse databases of emulator | Ernest | Doing | 20 | 7
Sprint Backlog | Backend | Presentation | Ernest | Doing | 15 | 8
Sprint Backlog | Backend | create analytics service | Ahmed | Doing | 20 | 9
Sprint Backlog | Backend | create logs service | Ahmed | Doing | 10 | 10
Sprint Backlog | Backend | implement deployment scripts | Ahmed | Doing | 0 | 11
[5 empty] | 65 | 12
Sprint Backlog | Mobile | implement activities, intents and layout | Ahmed | Doing | 60 | 13
Sprint Backlog | Mobile | implement navigation and buttons | Ahmed | Doing | 43 | 14
Sprint Backlog | Mobile | implement API calls | Ahmed | Doing | 36 | 15
Sprint Backlog | Mobile | implement graphics | Ahmed | Doing | 24 | 16
Sprint Backlog | Mobile | implement sensor integration | Ahmed | Doing | 19 | 17
Sprint Backlog | Mobile | implement themes and styling | Ahmed | Doing | 11 | 18
Sprint Backlog | Mobile | implement concurrency feature | Ahmed | Doing | 0 | 19
[5 empty] | 60 | 20
Sprint Backlog | Process Management | Review Scrum Standard, Model Bpmn | Ahmed | Doing | 55 | 21
Sprint Backlog | Process Management | Simulate the model | Ahmed | Doing | 43 | 22
Sprint Backlog | Process Management | Execute with services Bizagi studio | Ahmed | Doing | 31 | 23
Sprint Backlog | Process Management | execute process Mining with Celonis | Ahmed | Doing | 14 | 24
Sprint Backlog | Process Management | implement RPA in UIPath | Ahmed | Doing | 10 | 25
Sprint Backlog | Process Management | Integrate everything and Create Presentation | Ahmed | Doing | 0 | 26