## Sprint Backlog
PB Name | Task Name | Description and details | Check Out | Status | Remaining Effort [hr]
80
Sprint Backlog | Backend | Analyse dataset | Ahmed | Doing | 70
Sprint Backlog | Backend | dataset extract features | Ahmed | Doing | 65
Sprint Backlog | Backend | create inferer Service | Ahmed | Doing | 50
Sprint Backlog | Backend | create auth service | Ahmed | Doing | 40
Sprint Backlog | Backend | create emulator service | Ernest | Doing | 30
Sprint Backlog | Backend | analyse databases of emulator | Ernest | Doing | 20
Sprint Backlog | Backend | Presentation | Ernest | Doing | 15
Sprint Backlog | Backend | create analytics service | Ahmed | Doing | 20
Sprint Backlog | Backend | create logs service | Ahmed | Doing | 10
Sprint Backlog | Backend | implement deployment scripts | Ahmed | Doing | 0
65
Sprint Backlog | Mobile | implement activities, intents and layout | Ahmed | Doing | 60
Sprint Backlog | Mobile | implement navigation and buttons | Ahmed | Doing | 43
Sprint Backlog | Mobile | implement API calls | Ahmed | Doing | 36
Sprint Backlog | Mobile | implement graphics | Ahmed | Doing | 24
Sprint Backlog | Mobile | implement sensor integration | Ahmed | Doing | 19
Sprint Backlog | Mobile | implement themes and styling | Ahmed | Doing | 11
Sprint Backlog | Mobile | implement concurrency feature | Ahmed | Doing | 0
60
Sprint Backlog | Process Management | Review Scrum Standard, Model Bpmn | Ahmed | Doing | 55
Sprint Backlog | Process Management | Simulate the model | Ahmed | Doing | 43
Sprint Backlog | Process Management | Execute with services Bizagi studio | Ahmed | Doing | 31
Sprint Backlog | Process Management | execute process Mining with Celonis | Ahmed | Doing | 14
Sprint Backlog | Process Management | implement RPA in UIPath | Ahmed | Doing | 10
Sprint Backlog | Process Management | Integrate everything and Create Presentation | Ahmed | Doing | 0
Note on A1: Feature Name Product Owner: Add the story to the Sprint Backlog Develpment Team: Assign tasks for completion
Note on B1: Development Team: Add a short task name
Note on C1: Development Team: Describe the activity and add comments as needed. Add new lines on the same cell with [alt+enter]
Note on D1: Development Team: Select your name if you are working on it, remove it if you are not working on it anymore so anyone else can pull the activity.
Note on E1: Development Team: Select current status
Note on F1: Development Team: Fill the estimated remaining effort (how many horus of work are left to complete the task)