## Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING |  |  |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation | Michael - Andrea - Valerio | 7 | 7 | 0 | 2022-06-06 | 2022-07-15 | 40 | 100%
1.1 | Project idea | Michael - Andrea - Valerio | 1 | 1 | 0 | 2022-06-06 | 2022-06-10 | 5 | 100% | bar: WEEK 1 F to WEEK 2 F; WEEK 8 M to WEEK 8 F
1.2 | Decision of features | Michael - Andrea - Valerio | 1 | 1 | 0 | 2022-06-06 | 2022-06-10 | 5 | 100% | bar: WEEK 1 F to WEEK 2 F; WEEK 8 M to WEEK 8 F
1,3 | Choice of technologies | Michael - Andrea - Valerio | 1 | 1 | 0 | 2022-06-20 | 2022-06-24 | 5 | 100% | bar: WEEK 8 M to WEEK 8 F
1,4 | Definition of user stories | Michael - Andrea - Valerio | 1 | 1 | 0 | 2022-06-20 | 2022-06-24 | 5 | 100% | bar: WEEK 8 M to WEEK 8 F
1,5 | Creation of mockup | Michael - Andrea - Valerio | 1 | 1 | 0 | 2022-07-04 | 2022-07-08 | 5 | 100% | bar: WEEK 3 F; WEEK 8 M to WEEK 8 F
1,6 | Function Points | Michael - Andrea - Valerio | 1 | 1 | 0 | 2022-07-04 | 2022-07-08 | 5 | 100% | bar: WEEK 3 F; WEEK 8 M to WEEK 8 F
1,7 | COCOMO II | Michael - Andrea - Valerio | 1 | 1 | 0 | 2022-07-11 | 2022-07-15 | 5 | 100% | bar: WEEK 4 F to WEEK 5 F; WEEK 8 M to WEEK 8 F
2 | Sprint 1 | Michael - Andrea - Valerio | 42 | 42 | 0 | 2022-08-01 | 2022-08-12 | 12 | 100%
2.1 | Login seller | Michael - Valerio | 8 | 8 | 0 | 2022-08-01 | 2022-08-05 | 5 | 100% | bar: WEEK 6 F to WEEK 7 R; WEEK 8 F
2.2 | Login customer | Michael - Valerio | 8 | 8 | 0 | 2022-08-01 | 2022-08-05 | 5 | 100% | bar: WEEK 6 F to WEEK 7 R; WEEK 8 F
2.3 | Article creation | Michael - Valerio | 8 | 8 | 0 | 2022-08-08 | 2022-08-12 | 5 | 100% | bar: WEEK 7 F to WEEK 8 F
2.4 | Send message | Andrea | 18 | 18 | 0 | 2022-08-01 | 2022-08-12 | 12 | 100% | bar: WEEK 6 F to WEEK 8 F
2,5 | Bug fixing | Michael - Andrea - Valerio | 2 | 2 | 0 | 2022-08-01 | 2022-08-12 | 12 | 100% | bar: WEEK 6 F to WEEK 8 F
3 | Sprint 2 | Michael - Andrea - Valerio | 46 | 46 | 0 | 2022-08-15 | 2022-08-26 | 12 | 100%
3.1 | Article creation | Michael - Valerio | 8 | 8 | 0 | 2022-08-15 | 2022-08-19 | 5 | 100% | bar: WEEK 8 F to WEEK 9 R
3.2 | Buy product | Michael - Valerio | 18 | 18 | 0 | 2022-08-15 | 2022-08-26 | 12 | 100% | bar: WEEK 8 F to WEEK 10 R
3.3 | Track order | Andrea | 18 | 18 | 0 | 2022-08-15 | 2022-08-26 | 12 | 100% | bar: WEEK 8 F to WEEK 10 R
3.4 | Bug fixing | Michael - Andrea - Valerio | 2 | 2 | 0 | 2022-08-15 | 2022-08-26 | 12 | 100% | bar: WEEK 8 F to WEEK 10 R
4 | Sprint 3 | Michael - Andrea - Valerio | 18 | 18 | 0 | 2022-08-29 | 2022-09-08 | 11 | 100%
4.1 | Buy product | Michael - Valerio | 8 | 8 | 0 | 2022-08-29 | 2022-09-02 | 5 | 100% | bar: WEEK 8 M to WEEK 8 F; WEEK 10 F to WEEK 11 R
4.2 | Rate order | Michael - Valerio | 8 | 8 | 0 | 2022-08-29 | 2022-09-02 | 5 | 100% | bar: WEEK 8 M to WEEK 8 F; WEEK 10 F to WEEK 11 R
4.3 | Bug fixing | Michael - Andrea - Valerio | 2 | 2 | 0 | 2022-08-29 | 2022-09-08 | 11 | 100% | bar: WEEK 8 M to WEEK 8 F; WEEK 10 F to WEEK 12 W
|  |  | ESTIMATE | COMPLETED | REMAINING | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 113 | 113 | 0 | 1.8833 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[9 empty] | PLAN | 113 | 111.1167 | 109.2333 | 107.35 | 105.4667 | 103.5833 | 101.7 | 99.8167 | 97.9333 | 96.05 | 94.1667 | 92.2833 | 90.4 | 88.5167 | 86.6333 | 84.75 | 82.8667 | 80.9833 | 79.1 | 77.2167 | 75.3333 | 73.45 | 71.5667 | 69.6833 | 67.8 | 65.9167 | 64.0333 | 62.15 | 60.2667 | 58.3833 | 56.5 | 54.6167 | 52.7333 | 50.85 | 48.9667 | 47.0833 | 45.2 | 43.3167 | 41.4333 | 39.55 | 37.6667 | 35.7833 | 33.9 | 32.0167 | 30.1333 | 28.25 | 26.3667 | 24.4833 | 22.6 | 20.7167 | 18.8333 | 16.95 | 15.0667 | 13.1833 | 11.3 | 9.4167 | 7.5333 | 5.65 | 3.7667 | 1.8833
[9 empty] | ESTIMATE | 113 | 113 | 113 | 113 | 113 | 111 | 111 | 111 | 111 | 111 | 109 | 109 | 109 | 109 | 109 | 107 | 107 | 107 | 107 | 107 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 101 | 99 | 97 | 94 | 90 | 84 | 78 | 75 | 70 | 64 | 61 | 56 | 48 | 44 | 39 | 35 | 30 | 25 | 22 | 19 | 18 | 16 | 13 | 10 | 9 | 7 | 5 | 2 | 0 | 0 | 4571
[8 empty] | Enter hours completed per day ----> | HRS COMPLETED | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 2 | 3 | 4 | 6 | 6 | 3 | 5 | 6 | 3 | 5 | 8 | 4 | 5 | 4 | 5 | 5 | 3 | 3 | 1 | 2 | 3 | 3 | 1 | 2 | 2 | 3 | 2 | 0 | 0 | 113
[9 empty] | HRS REMAINING | 113 | 113 | 113 | 113 | 111 | 111 | 111 | 111 | 111 | 109 | 109 | 109 | 109 | 109 | 107 | 107 | 107 | 107 | 107 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 101 | 99 | 97 | 94 | 90 | 84 | 78 | 75 | 70 | 64 | 61 | 56 | 48 | 44 | 39 | 35 | 30 | 25 | 22 | 19 | 18 | 16 | 13 | 10 | 9 | 7 | 5 | 2 | 0 | 0 | 0 | 4458
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Sprint 1
Sprint 1
Name |  | First Sprint |  |  |  | 0
Goal |  | Login-Article-Message |  | Duration | 10 working days
Start Date |  | 2022-08-01 |  | Things | 5 things
End Date |  | 2022-08-12 |  | Story Points | 20 points
days left
Sprint Metrics
Things Planned |  | 5 | Key Achievements | Process improvement of previous sprint achieved (faster internet connection on Reading location) Process improvement of current sprint partly achieved (optimized local dev environment)
Points Planned |  | 20
Story Points done |  | #NAME?
Story Points left: |  | #NAME?
Sprint Backlog
Things (5) | Type | Story Points (20) | Description
Login seller | story | 3 | As a seller, I want to be able to login, so that I can use the services of GreenThumb.
Login customer | story | 3 | As a customer, I want to be able to login, so that I can use the services of GreenThumb.
Article creation | story | 3 | As a seller, I want to be able to add articles to my shop, so that I can sell my products.
Send message | story | 2 | As a customer, I want to be able to chat with a seller, so that I can have info about a product.
Bug fixing | bug | 9 | Fix bug.

## Sprint 2
Sprint 2
Name |  | Second Sprint |  |  |  | 0
Goal |  | Article-Buy-Tracking |  | Duration | 10 working days
Start Date |  | 2022-08-15 |  | Things | 4 things
End Date |  | 2022-08-26 |  | Story Points | 17 points
days left
Sprint Metrics
Things Planned |  | 3 | Key Achievements | Process improvement of previous sprint achieved (faster internet connection on Reading location) Process improvement of current sprint partly achieved (optimized local dev environment)
Points Planned |  | 17
Story Points done |  | #NAME?
Story Points left: |  | #NAME?
Sprint Backlog
Things (3) | Type | Story Points (17) | Description
Article creation | story | 4 | As a seller, I want to be able to add articles to my shop, so that I can sell my products.
Buy product | story | 5 | As a customer, I want to be able to buy a product, so that I can have a new plant in my garden.
Track order | story | 3 | As a customer, I want to be able to track in real time my order, so that I can know at every moment where is my article.
Bug fixing | bug | 9 | Fix bug.

## Sprint 3
Sprint 3
Name |  | Third Sprint |  |  |  | 0
Goal |  | Buy-Rate-Bug |  | Duration | 9 working days
Start Date |  | 2022-08-29 |  | Things | 3 things
End Date |  | 2022-09-08 |  | Story Points | 16 points
days left
Sprint Metrics
Things Planned |  | 3 | Key Achievements | Process improvement of previous sprint achieved (faster internet connection on Reading location) Process improvement of current sprint partly achieved (optimized local dev environment)
Points Planned |  | 16
Story Points done |  | #NAME?
Story Points left: |  | #NAME?
Sprint Backlog
Things (3) | Type | Story Points (16) | Description
Buy product | story | 5 | As a customer, I want to be able to buy a product, so that I can have a new plant in my garden.
Rate order | story | 2 | As a customer, I want to be able to rate my order, so that I can help other users to choose a seller.
Bug fixing | bug | 9 | Fix bug.