## Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  | WEEK 2 |  |  | WEEK 3 |  |  | WEEK 4 |  |  | WEEK 5
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | M | T | W | M | T | W | M | T | W | M | T | W
1 | General infrastructure |  | 11 | 11 | 0 |  |  |  |  | 100%
1.1 | Create Docker infrastructure | Andrea M. | 11 | 11 | 0 | 1 | 2022-08-01 | 2022-08-03 | 3 | 100%
2 | Admin infrastructure implementation |  | 41 | 41 | 0 |  |  |  |  | 100%
2.1 | Address Issues | ALL | 3 | 3 | 0 | 2 | 2022-08-08 | 2022-08-08 | 1 | 100%
2.2 | Configure Admin Nginx | Andrea M. | 5 | 5 | 0 | 2 | 2022-08-08 | 2022-08-08 | 1 | 100%
2.3 | Create Admin Server | Giorgia R. | 10 | 10 | 0 | 2 | 2022-08-08 | 2022-08-09 | 2 | 100%
2.4 | Create Admin Interface | Andrea R. | 10 | 10 | 0 | 2 | 2022-08-09 | 2022-08-10 | 2 | 100%
2.5 | Create DB Interaction Function | Alessandro M. | 7 | 7 | 0 | 2 | 2022-08-09 | 2022-08-10 | 2 | 100%
2.6 | Create Connection to Message Broker | Giorgia R. | 6 | 6 | 0 | 2 | 2022-08-09 | 2022-08-10 | 2 | 100%
3 | User infrastructure implementation |  | 43 | 43 | 0 |  |  |  |  | 100%
3.1 | Address Issues | ALL | 2 | 2 | 0 | 2 | 2022-08-22 | 2022-08-22 | 1 | 100%
3.2 | Fix the Infrastructure | Andrea M. | 3 | 3 | 0 | 3 | 2022-08-22 | 2022-08-23 | 2 | 100%
3.3 | Configure User Nginx | Andrea M. | 4 | 4 | 0 | 3 | 2022-08-22 | 2022-08-23 | 2 | 100%
3.4 | Create User Server | Andrea R. | 13 | 13 | 0 | 3 | 2022-08-22 | 2022-08-24 | 3 | 100%
3.5 | Create User Interface | Alessandro M. | 15 | 15 | 0 | 3 | 2022-08-23 | 2022-08-24 | 2 | 100%
3.6 | Create Connection to Message Broker | Giorgia R. | 6 | 6 | 0 | 3 | 2022-08-23 | 2022-08-24 | 2 | 100%
4 | Final touches |  | 27 | 27 | 0 |  |  |  |  | 100%
4.1 | Address Issues | ALL | 10 | 10 | 0 | 4 | 2022-08-29 | 2022-08-31 | 3 | 100%
4.2 | Bug Fixes | ALL | 17 | 17 | 0 | 4 | 2022-08-29 | 2022-08-31 | 3 | 100%
5 | Cloud Deployment |  | 21 | 21 | 0 |  |  |  |  | 100%
5.1 | Understand Feasability | Andrea R., Andrea M. | 3 | 3 | 0 | 5 | 2022-09-05 | 2022-09-05 | 1 | 100%
5.2 | Cloud Adjustments | Andrea R., Andrea M. | 7 | 7 | 0 | 5 | 2022-09-05 | 2022-09-06 | 2 | 100%
5.3 | Issue Solving | Giorgia R. | 6 | 6 | 0 | 5 | 2022-09-06 | 2022-09-07 | 2 | 100%
5.4 | Bug Fixes | Alessandro M. | 5 | 5 | 0 | 5 | 2022-09-07 | 2022-09-07 | 1 | 100%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 143 | 143 | 0 | 15 | 9.5333 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 143 | 133.4667 | 123.9333 | 114.4 | 104.8667 | 95.3333 | 85.8 | 76.2667 | 66.7333 | 57.2 | 47.6667 | 38.1333 | 28.6 | 19.0667 | 9.5333
[10 empty] | ESTIMATE | 143 | 139 | 135 | 132 | 119 | 104 | 91 | 80 | 65 | 48 | 38 | 29 | 21 | 16 | 8 | 1123
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 4 | 4 | 3 | 13 | 15 | 13 | 11 | 15 | 17 | 10 | 9 | 8 | 5 | 8 | 8 | 143
[10 empty] | HRS REMAINING | 139 | 135 | 132 | 119 | 104 | 91 | 80 | 65 | 48 | 38 | 29 | 21 | 16 | 8 | 0 | 1001

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG | [5 empty] | 143
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
|  | PROJECT | PROJECT
1 | 1 | General Infrastructure | Create Docker Infrastructure | Build the rough structure of the docker compose file and the base configuration of the main services | Andrea M. | 11 | Completed |  | Not Started | 1
[9 empty] | In Progress | 2
1 | 2 | General | Address Issues | Address the issues/doubts discovered in the previous sprint | ALL | 3 | Completed |  | Completed | 3
2 | 2 | General Infrastructure | Configure Admin Nginx | Define the configuration to access to the admin panel | Andrea M. | 5 | Completed |  |  | 4
2 | 2 | Admin - Side | Create Admin Server | Define the basic API of the Admin Server | Giorgia R. | 10 | Completed |  |  | 5
2 | 2 | Admin - Side | Create Admin Interface | Implement the basic web interface for the admin | Andrea R. | 10 | Completed | SSL missing |  | 6
2 | 2 | General Infrastructure | Create DB Interaction Function | Create the necessaries functions to interact with the choosen database | Alessandro M. | 7 | Completed | Still need to manage concurrency |  | 7
3 | 2 | General Infrastructure | Create Connection to Message Broker | Make the admin server write on the message broker | Giorgia R. | 6 | Completed |  |  | 8
9
1 | 3 | General | Address Issues | Address the issues/doubts discovered in the previous sprint | ALL | 2 | Completed |  |  | 10
1 | 3 | General Infrasturcture | Fix the Infrastructure | Refine the infrastructure build, adjusting the parameters according to how the development evolved | Andrea M. | 3 | Completed |  |  | 11
2 | 3 | General Infrastructure | Configure User Nginx | Define the configuration enabling load balancing for the user | Andrea M. | 4 | Completed |  |  | 12
2 | 3 | User - Side | Create User Server | Implement the template for the implementation of the websocket of the worker | Andrea R. | 13 | Completed |  |  | 13
2 | 3 | User - Side | Create User Interface | Implement the basic web interface for the user | Alessandro M. | 15 | Completed |  |  | 14
3 | 3 | General Infrastructure | Create Connection to Message Broker | Make the worker receive the messages published on the message broker | Giorgia R. | 6 | Completed |  |  | 15
16
1 | 4 | General | Address Issues | Address the issues/doubts discovered in the previous sprint | ALL | 10 | Completed |  |  | 17
1 | 4 | Test | Bug Fixes | Try to discover and fix bugs | ALL | 17 | Completed |  |  | 18
19
1 | 5 | Cloud Deployment | Understand Feasability | Define the feasability of a cloud deployment | Andrea R., Andrea M. | 3 | Completed |  |  | 20
1 | 5 | Cloud Deployment | Cloud Adjustments | Adjust the existing files to make them cloud compatible | Andrea R., Andrea M. | 7 | Completed
1 | 5 | Cloud Deployment | Issue Solving | Fix the issues that rose up | Giorgia R. | 6 | Completed
1 | 5 | Test | Bug Fixes | Try to discover and fix bugs | Alessandro M. | 5 | Completed

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED
User-Interface | As a User I want to have a web interface that I can access so that I can play the game | The Team | 2022-01-08
Nickname | As a User I want to have field in the main page where I can add a nickname | The Team | 2022-01-08
Question | As a User I want to have I clear way to understand that I am waiting for a question | The Team | 2022-01-08
Answer | As a User I want to have an easy way to answer the questions asked in the tv program | The Team | 2022-01-08
Final score | As a User I want to see my final score when the game ends | The Team | 2022-01-08
Multiple games | As a User I want to be able to play multiple games with different nickname | The Team | 2022-01-08
Problem | As a User I want to be able to access again the game in case for some reason I exited | The Team | 2022-03-08
Game managing | As an Admin I want to have an interface that allows me to manage the game | The Team | 2022-01-08
Start game | As an Admin I want to have in the interface the ability to start a new game | The Team | 2022-01-08
Correct answer | As an Admin I want to see the next question number and to select the correct answer from it | The Team | 2022-01-08
Admin-interface | As an Admin I want a dedicated interface completely disconnected from the users' one | The Team | 2022-01-08
End game | As an Admin I want the ability to end the game so to notify the players of their score | The Team | 2022-01-08
Score's overview | As an Admin I want to have an overview of the score of the actually playing users | The Team | 2022-01-08
Answers' overview | As an Admin I want to have an overview of the answers to the last question done | The Team | 2022-01-08
Problem solving | As an Admin I want some feature that help me avoid making mistakes such as starting a new question too soon | The Team | 2022-03-08
Cloud | As a Admin I way the system to run on cloud so that I can monitor and balance at need | The Team | 29/8/2022