## Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | END DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  | WEEK 2 |  |  | WEEK 3 |  |  | WEEK 4 |  |  | WEEK 5
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | W | T | W | M | T | W | M | T | W | M | T | W
1 | Schema infrastructure | ALL | 8 | 8 | 0 | 1 | 2023-04-26 | 2023-04-27 | 2 | 100%
2 | Interface API 'url_analyzer' | Matteo Feliziani | 8 | 8 | 0 | 1 | 2023-04-27 | 2023-04-28 | 2 | 100%
3 | Database Inizialization | Guido Sameuele De Rosa | 6 | 6 | 0 | 1 | 2023-04-27 | 2023-04-27 | 1 | 100%
4 | User front-end | Simone Gennenzi | 5 | 5 | 0 | 1 | 2023-04-28 | 2023-04-28 | 1 | 100%
5 | Admin front-end | Simone Gennenzi | 5 | 5 | 0 | 2 | 2023-04-29 | 2023-04-29 | 1 | 100%
6 | Interface API 'text_analyzer' | Matteo Feliziani | 8 | 8 | 0 | 2 | 2023-04-29 | 2023-04-30 | 2 | 100%
7 | Create RabbitMQ queue user-admin | Davide Gentili | 8 | 8 | 0 | 2 | 2023-04-29 | 2023-04-30 | 2 | 100%
8 | Login functionality - User | Simone Gennenzi | 10 | 10 | 0 | 2 | 2023-04-30 | 2023-05-01 | 2 | 100%
9 | Login functionality - Admin | Simone Gennenzi | 15 | 15 | 0 | 3 | 2023-05-15 | 2023-05-17 | 3 | 100%
10 | Fix login bugs | ALL | 8 | 8 | 0 | 3 | 2023-05-15 | 2023-05-15 | 1 | 100%
11 | Integration of the database | Guido Sameuele De Rosa | 10 | 10 | 0 | 3 | 2023-05-16 | 2023-05-17 | 2 | 100%
12 | First Docker development | Matteo Feliziani | 6 | 6 | 0 | 3 | 2023-05-16 | 2023-05-17 | 2 | 100%
13 | text_analyzer logic | Davide Gentili | 15 | 15 | 0 | 3 | 2023-05-15 | 2023-05-17 | 3 | 100%
14 | url_analyzer logic | Davide Gentili | 7 | 7 | 0 | 4 | 2023-05-22 | 2023-05-23 | 2 | 100%
15 | First general test | ALL | 4 | 4 | 0 | 4 | 2023-05-22 | 2023-05-22 | 1 | 100%
16 | Fix first-test bugs | ALL | 5 | 5 | 0 | 4 | 2023-05-23 | 2023-05-23 | 1 | 100%
17 | Implement RabbitMQ queue persistence | Davide Gentili | 7 | 7 | 0 | 4 | 2023-05-23 | 2023-05-24 | 2 | 100%
18 | Finalize the docker-compose file | Guido Sameuele De Rosa | 4 | 4 | 0 | 4 | 2023-05-24 | 2023-05-24 | 1 | 100%
19 | Second general test | ALL | 5 | 5 | 0 | 5 | 2023-06-03 | 2023-06-03 | 1 | 100%
20 | Fix second-test bugs | ALL | 15 | 15 | 0 | 5 | 2023-06-03 | 2023-06-05 | 3 | 100%
21 | Final general test | ALL | 5 | 5 | 0 | 5 | 2023-06-04 | 2023-06-05 | 2 | 100%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 164 | 164 | 0 | 15 | 10.9333 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 164 | 153.0667 | 142.1333 | 131.2 | 120.2667 | 109.3333 | 98.4 | 87.4667 | 76.5333 | 65.6 | 54.6667 | 43.7333 | 32.8 | 21.8667 | 10.9333
[10 empty] | ESTIMATE | 164 | 160 | 146 | 137 | 124 | 111 | 106 | 88 | 70 | 52 | 45 | 33 | 25 | 15 | 7.5 | 1236
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 4 | 14 | 9 | 13 | 13 | 5 | 18 | 18 | 18 | 7 | 12 | 8 | 10 | 7.5 | 7.5 | 164
[10 empty] | HRS REMAINING | 160 | 146 | 137 | 124 | 111 | 106 | 88 | 70 | 52 | 45 | 33 | 25 | 15 | 7.5 | 0 | 1097

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG | [5 empty] | 165
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
|  | PROJECT | PROJECT
3 | 1 | General Infrastructure | Schema infrastructure | Draw the blocks-schema representing the infrastructure of the application | ALL | 8 | Completed |  | Not Started | 1
[9 empty] | In Progress | 2
2 | 1 | Microservices | Interface API url_analyzer | Develop the API interfacee of the url_analyzer microservice | Matteo Feliziani | 8 | Completed |  | Completed | 3
1 | 1 | User - side | User front-end | Create the web interfaces for the user | Simone Gennenzi | 6 | Completed |  |  | 4
2 | 1 | Microservices | Database inizialization | Initialize the database to store user information | Guido Samuele De Rosa | 5 | Completed |  |  | 5
1 | 2 | Admin - Side | Admin Front-end | Create the web interfaces for the admin | Simone Gennenzi | 6 | Completed |  |  | 6
2 | 2 | Microservices | Interface API text_analyzer | Develop the API interfaces of the text_analyzer microservice | Matteo Feliziani | 8 | Completed |  |  | 7
2 | 2 | General Infrastructure | Create RabbitMQ queue user-admin | Create the RabbitMQ queue to allow the admin to see the email's user analyses | Davide Gentili | 8 | Completed |  |  | 8
9
3 | 2 | User - Side | Login functionality - User | Build the login functionality to allow the user to login and sign up to the application | Simone Gennenzi | 15 | Completed |  |  | 10
3 | 3 | Admin - Side | Login functionality - Admin | Build the login functionality to allow the admin to login and sign up to the application | Simone Gennenzi | 10 | Completed |  |  | 11
1 | 3 | General Infrastructure | Fix login bugs | Fix bugs discovered in the previous tasks | ALL | 8 | Completed |  |  | 12
1 | 3 | General Infrastructure | Integration of the database | Fix databases issues | Guido Samuele De Rosa | 10 | Completed |  |  | 13
3 | 3 | General Infrastructure | First Docker development | Compose the docker infrastructure of the application | Matteo Feliziani | 6 | Completed |  |  | 14
3 | 3 | Microservices | text_analyzer logic | Implement the logic of the 'text_analyzer' based on ML algorithm | Davide Gentili | 15 | Completed |  |  | 15
16
2 | 4 | Microservices | url_analyzer logic | Implement the logic of the 'url_analyzer' trhough external requests | Davide Gentili | 7 | Completed |  |  | 17
2 | 4 | Test | First general test | Test the overall functionalities of the application | ALL | 4 | Completed |  |  | 18
19
1 | 4 | Test | Fix first-test bugs | Fix bugs discovered in the previous tasks | ALL | 5 | Completed |  |  | 20
1 | 4 | General Infrastructure | Implement RabbitMQ queue persistence | Make the RabbitMQ queue from user to admin persistent | Davide Gentili | 7 | Completed
2 | 5 | General Infrastructure | Finalize docker-compose file | Finalize the docker compose file | Guido Samuele De Rosa | 4 | Completed
2 | 5 | Test | Second general test | Test the overall functionalities of the application for the second time | ALL | 5 | Completed
1 | 5 | Test | Fix second-test bugs | Fix bugs discovered in the previous tasks | ALL | 15 | Completed
3 | 5 | Test | Final general test | Last test of the overall functionalities of the application | ALL | 5 | Completed

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED
User Registration | As a User I want to have a page where i can sign up | The Team | 2023-04-26
User Login | As a User I want to have a page where i can sign in | The Team | 2023-04-26
User-Interface | As a User I want to have a web interface where I can insert email's info | The Team | 2023-04-26
Log out | As a User I want to be able to log out from the site | The Team | 2023-04-26
Email's danger score | As a User I want to see the email's danger score | The Team | 2023-05-22
History of emails | As a User I want to see the history of all emails i have sent | The Team | 2023-05-22
Admin-interface | As an Admin I want a dedicated interface completely disconnected from the users' one | The Team | 2023-04-26
Admin Registration | As a Admin I want to have a page where i can sign up | The Team | 2023-04-26
Admin Login | As a Admin I want to have a page where i can sign in | The Team | 2023-04-26
Log out | As a User I want to be able to log out from the site | The Team | 2023-04-26
Email's overview | As an Admin I want to have an overview of the danger's score of the emails sent | The Team | 2023-04-30